## Project Summary
1204 DUNSTAN RD · RENOVATION PROJECT BUDGET
Houston, TX ¦ Active Renovation ¦ Budget as of 2025
DEAL SUMMARY
Purchase Price |  | 75200 |  | ARV (Low Estimate) |  | 215000
Net Acquisition Cost |  | 81125 |  | ARV (High Estimate) |  | 230000
Pre-Reno Appraised Value |  | 160000 |  | Projected Profit (Low) |  | 73349.4167
Total Renovation Budget |  | 60525.5833 |  | Projected Profit (High) |  | 88349.4167
TOTAL ALL-IN COST |  | 141650.5833 |  | Return on Cost (Low) |  | 51.78%
Instant Equity (Pre-Reno) |  | 160000 |  | Return on Cost (High) |  | 62.37%
Color Key: Blue text = Hardcoded input ¦ Black = Formula ¦ Green = Cross-sheet link ¦ PERT = (Opt + 4×ML + Pess) ÷ 6 hrs × $25/hr
HOUSE ACQUISITION
Description | Amount | — | — | Total | Notes / Assumptions | Reference
Property Purchase Price | 75200 | — | — | 75200 | Agreed sale price | Purchase Agreement
Loan / Mortgage Amount | 71440 | — | — | 71440 | Financed portion (informational) | Lender / Loan Docs
Down Payment (Cash Equity) | 9685 | — | — | 9685 | Purchase price minus loan | Calculated
Total w/ All Closing Fees | 83375 | — | — | 83375 | Includes title, escrow & all fees | Settlement Statement
Seller Contribution | 2250 | — | — | 2250 | Seller-paid closing cost credit | Settlement Statement
NET ACQUISITION COST
CONTRACTOR BIDS (Material & Labor Included in Bid Price)
Description | Material Cost | Labor Hours | Labor Cost | Total Cost | Notes / Assumptions | Source / Detail
Foundation + Flatwork (Driveway & Sidewalk) | Bundled | Bundled | 10627 | 10627 | Incl. $2,000 discount; driveway & sidewalk | Contractor Bid
New Roof (incl. Tear-Off) | Bundled | Bundled | 8267.25 | 8267.25 | Incl. $1,200 discount; full tear-off & replace | Contractor Bid
Electrical Panel Upgrade (100A → 200A) | Bundled | Bundled | 4300 | 4300 | Service upgrade from 100A to 200A | Contractor Bid
CONTRACTOR SUBTOTAL |  |  |  | 23194.25
EXTERIOR WORK (Material + Labor @ $25/hr)
Description | Material Cost | Labor Hours | Labor Cost | Total Cost | Notes / Assumptions | Source / Detail
Siding / Trim | 1100 | 27.1667 | 679.1667 | 1779.1667 | 55 hrs fixed (140-hr package); panels + trim | PERT sheet
Sheathing + Waterproofing | 214 | 30 | 750 | 964 | Fixed 18 hrs (140-hr package); ForceField sheathing + waterproof membrane | PERT sheet
Eave | 350 | 25 | 625 | 975 | 25 hrs fixed; fascia & soffit installation | PERT sheet
Insulation | 500 | 20.8333 | 520.8333 | 1020.8333
Exterior Paint | 365 | 38 | 950 | 1315 | PERT estimate; ~1,050 sq ft; all supplies included | PERT sheet
Windows / New Patio Door | 1500 | 60.8333 | 1520.8333 | 3020.8333 | 22 hrs fixed (140-hr package); replacement windows + patio door | PERT sheet
Fix Damaged Studs | 100 | 25.8333 | 645.8333 | 745.8333 | 25 hrs fixed (140-hr package); stud repair & sistering | PERT sheet
New Fence | 5750 | 29.3333 | 733.3333 | 6483.3333 | PERT estimate; 5 fence pipe sections; full perimeter | PERT sheet
EXTERIOR SUBTOTAL |  | 257 | 6425 | 16304
INTERIOR & RENOVATION (Material + Labor @ $25/hr)
Description | Material Cost | Labor Hours | Labor Cost | Total Cost | Notes / Assumptions | Source / Detail
Water Heater | 600 | 6.5 | 162.5 | 762.5 | 40-gal tank material | PERT sheet
Electrical (Rough-In) | 3000 | 80 | 2000 | 5000 | Full rough-in wiring | PERT sheet
Doors | 385 | 12.3333 | 308.3333 | 693.3333 | 5 slabs @$55 + 1 pre-cased @$110 | PERT sheet
Bathroom Tile | 300 | 12.3333 | 308.3333 | 608.3333 | 25 sq ft × $12/sq ft | PERT sheet
Interior Paint | 400 | 54.3333 | 1358.3333 | 1758.3333 | Walls 6,000 + doors 172 + trim 200 sq ft | PERT sheet
HVAC | 6500 | 41.3333 | 1033.3333 | 7533.3333 | Equipment/material only; installation PERT | PERT sheet
Shed Remove | 100 | 8 | 200 | 300 | Demo & haul; 6 hrs fixed @ $25/hr | PERT sheet
Covered Deck | 689 | 21.3333 | 533.3333 | 1222.3333 | 19'×16'; metal roof + deck boards + paint | PERT sheet
Garage Ceiling Drywall | 135 | 10.3333 | 258.3333 | 393.3333 | 12'×18'; drywall + joint compound | PERT sheet
Stackable Dryer to Washing Machine Location | 410 | 29.3333 | 733.3333 | 1143.3333 | Add vent in wall, running to outside | PERT sheet
Misc. Fixtures | 1000 | 25 | 612.5 | 1612.5 | 3 faucets + ceiling fans + smoke detectors | PERT sheet
INTERIOR SUBTOTAL |  | 300.8333 | 7508.3333 | 21027.3333
|  | Total Labor Hrs | Total Labor Cost | Total Project Cost
★ TOTAL PROJECT COST |  | 557.8333 | 13933.3333 | 60525.5833

## PERT Labor Estimates
PERT LABOR COST ESTIMATES
Fixed hours override PERT where specified ¦ Siding + Sheathing + Insulation + Windows + Studs = 140 hrs fixed ¦ Labor $ = Hours × Rate
LABOR RATE ($/hr): |  |  | 25
Trade / Item | Fixed Hrs (override) | Opt (hrs) | Most Likely (hrs) | Pess (hrs) | PERT Hours | Labor Cost (@ $25/hr) | Assumptions / Notes
— EXTERIOR WORK —
Siding / Trim | — | 20 | 27 | 35 | 27.1667 | 679.1667 | Fixed 55 hrs — siding panels, trim install (140-hr pkg)
Sheathing + WP | — | 20 | 30 | 40 | 30 | 750 | Fixed 18 hrs — sheathing + waterproof membrane (140-hr pkg)
Eave | — | 20 | 25 | 30 | 25 | 625 | Fixed 25 hrs — carpenter, fascia & soffit
Exterior Paint | — | 20 | 36 | 64 | 38 | 950 | Painter crew; pressure wash, prime, 2-coat spray
Insulation | — | 15 | 20 | 30 | 20.8333 | 520.8333 | Fixed 20 hrs — batt/blow-in whole house (140-hr pkg)
Windows / Patio Door | — | 50 | 60 | 75 | 60.8333 | 1520.8333 | Fixed 22 hrs — remove, install, seal, trim (140-hr pkg)
Fix Damaged Studs | — | 5 | 25 | 50 | 25.8333 | 645.8333 | Fixed 25 hrs — stud repair, sistering, blocking (140-hr pkg)
New Fence | — | 16 | 28 | 48 | 29.3333 | 733.3333 | Fence crew; panels, rails, gates, hardware
— INTERIOR & RENOVATION —
Water Heater | — | 3 | 6 | 12 | 6.5 | 162.5 | Plumber: connections, drain pan, flush & test
Electrical (Rough-In) | — | 40 | 80 | 120 | 80 | 2000 | Licensed electrician; rough-in wiring & devices
Doors | — | 6 | 12 | 20 | 12.3333 | 308.3333 | Carpenter; hang, shim, hardware — all 6 doors
Bathroom Tile | — | 6 | 12 | 20 | 12.3333 | 308.3333 | Tile setter; prep, set 25 sq ft, grout, seal
Interior Paint | — | 30 | 52 | 88 | 54.3333 | 1358.3333 | Painter; walls/ceiling, trim, doors
HVAC | — | 24 | 40 | 64 | 41.3333 | 1033.3333 | HVAC tech; refrigerant, ductwork, startup
Shed Remove |  | 4 | 8 | 12 | 8 | 200 | Fixed 6 hrs — demo, load, haul
Gazebo | — | 12 | 20 | 36 | 21.3333 | 533.3333 | Carpenter; framing, decking, metal roof
Garage Drywall | — | 6 | 10 | 16 | 10.3333 | 258.3333 | Drywall finisher; hang, tape, mud, sand, prime
Laundry Rebuild | — | 16 | 28 | 48 | 29.3333 | 733.3333 | Framer + plumber; wall framing + plumbing rough-in
Misc. Fixtures | — | 12 | 25 | 35 | 24.5 | 612.5 | Framer + plumber; wall framing + plumbing rough-in
TOTAL ESTIMATED LABOR |  |  |  |  | 532.8333 | 13320.8333

## Line Item Details
LINE ITEM COST BREAKDOWNS
SIDING / TRIM (64 linear ft)
Component/Description | Quantity | Unit Cost | Line Total | Notes
Siding Panels
Trim Material | — | — | 396 | Trim to reach $900 total
Subtotal |  |  | 396
SHEATHING + WATERPROOFING
Component/Description | Quantity | Unit Cost | Line Total | Notes
ForceField Plywood Sheathing
Waterproof Membrane / Wrap | — | — | 164 | Housewrap + tape
Plywood Seam Tape | — | — | 50 | Seam sealing
Subtotal |  |  | 214
EXTERIOR PAINT (~1,050 sq ft)
Component/Description | Quantity | Unit Cost | Line Total | Notes
Siding Coverage
Eave Coverage | 430 sq ft | — | TBD
Gable End | 140 sq ft | — | TBD | Total: 1,050 sq ft
Paint
Airless Paint Sprayer
Caulk | — | — | 30
Painter's Tape
Rosin Paper | — | — | 20
Paint Brush
Additional Paint (balance)
Subtotal |  |  | 50
DOORS (6 Total)
Component/Description | Quantity | Unit Cost | Line Total | Notes
Interior Slab Door 24×80
Pre-Cased Door 24×80 | 1 | 110 | 110 | Incl. casing
Subtotal |  |  | 110
INTERIOR PAINT
Component/Description | Quantity | Unit Cost | Line Total | Notes
Paint — Walls & Ceiling
Paint — Doors & Trim
Subtotal |  |  | 0
BATHROOM TILE (54"×59")
Component/Description | Quantity | Unit Cost | Line Total | Notes
Wall/Floor Tile | 25 sq ft | 12 | 300 | 25 × $12
Toilet (26" rough-in) | 1 | — | TBD
Vanity (28×21") | 1 | — | TBD
Bathroom Mirror
Bathroom Light Fixture
Subtotal |  |  | 300
LAUNDRY REBUILD (24'×8' wall)
Component/Description | Quantity | Unit Cost | Line Total | Notes
Insulation (0.6 × 192 sq ft) | 192 sq ft | — | 115 | Batt insulation for walls
Drywall | — | — | 150
Joint Compound (Mud) | — | — | 20
Drywall Screws | — | — | 50
Plumbing Rough-In | — | — | 45
Framing Studs | — | — | 30
Subtotal |  |  | 410
GAZEBO (19'×16' = 304 sq ft)
Component/Description | Quantity | Unit Cost | Line Total | Notes
Metal Roof Panels | 20 panels | 30 | 600 | 10'×2' panels
Deck Boards 10' | 5 boards | 7.78 | 38.9
Deck Board 16' | 1 board | 12.5 | 12.5
Deck Paint | — | — | 37
Subtotal |  |  | 688.4
GARAGE DRYWALL (12'×18')
Component/Description | Quantity | Unit Cost | Line Total | Notes
Drywall Sheets | — | — | 115
Joint Compound | — | — | 20
Subtotal |  |  | 135
MISC. FIXTURES
Component/Description | Quantity | Unit Cost | Line Total | Notes
Faucets | 3 | 100 | 300 | $100 ea avg
Ceiling Fans | — | — | 300
Smoke Detectors | — | — | 120
Door Handles | 5 | — | TBD
Bathroom Lights | 2 | — | TBD
Bathroom Mirrors | 2 | — | TBD
Subtotal |  |  | 720